## Sheet1
CRID | Description | Type | Risks | Actions
CR_01 | Moataz left the team and Mohammad replaced his poistion. | Internal | 1- The assigned tasks for Moataz (class diagram update) may not be done in it’s time. 2- changes on the class diagram might be needed and no one will be able to make it because moataz used his own email on the tools. 3- Mohamed might be not familiar with some of our tools (Trello). 4- Future tasks for moataz might not be reassigned. 5- Work done by moataz all over the project ex: (PMP, class diagram, add article feature, ....) might not be totally understood by other team members. | 1-The team will communicate with Moataz maxmium one hour for in the following two weeks (till 25-5). 2- Moataz will finish his assigned tasks before leaving. 3- Moataz will give us access to the class diagram file on the tool. 4- Mohamed will get a training in our scheduling tool (trello). 5- All future tasks will be reassigned. 6- Moataz will hand over all his done tasks proffesionally.
CR_02 | Admins can not edit the articles | External | 1- Some work products migh not be updated correctly. 2- The current tasks assigned might need to be reconsidered. 3- delay in the project schedule and increase of the cost due to that so much additional work will be needed to update all documents and work products. | 1-The RTM will be used to define the impact of this risk on work products. SRS: Feature 3.1.5 will be deleted CRS: features 5.1-5.2 will bed eleted Class diagram: editcontent()-editallcontent() functions will be deleted. Admin sequence diagram: 4.0-4.8 will be removed User sequence diagram: 5.0-5.8 will be removed Use case diagram: Edit-Edit all will be removed RTM: edit features(32-38) will be deleted 2- Team members will stop working on the current tasks until impact analysis is done. 3- Customer will be informed of the additional time and cost will be needed due to this change request.